## Main
Today | Copy this doc and follow the link below for instructions. |  | 37 |  | 26 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | This doc is: http://bit.ly/IGDPD_BDC_Example
2016-12-13 | http://bit.ly/IGDPD_BDC_Instructions |  | Hours | Hours | Hours |  |  | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed
Rank | Task | Assn | Est. | Worked | Rem. |  |  | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | Detailed Information | #
Task Assignments
| — Game Physics — | [25 empty] | 5
1 | Movement | J | 3 | 3 | 1 |  | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 6
1 | Basic Collisions | T | 3 | 3 | 1 |  | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 7
2 | Dash Function | T | 2 | 3 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 8
1 | Adding Force on Collision | T | 4 | 5 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 9
2 | Debugging Physics | J | 4 | 6 | 2 |  | 4 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 10
11
12
1 |  |  | 2 | 3 | 0 |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13
|  |  | 1 |  | 1 |  | 1 | [19 empty] | 14 | bar: 2018-11-28 to 2018-11-28
| --- Art --- | [25 empty] | 15
3 | Particle System | T | 3 | 3 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 16
3 | Ball Materials | T | 1 | 1 | 1 |  | 1 | [19 empty] | 17 | bar: 2018-11-28 to 2018-11-28
1 | Custom Arenas | T | 5 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 18
2 | Game Screens (Start, Selections, Results) | J | 4 | 6 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  | 19
3 | Skyboxes | T | 1 | 1 | 1 |  | 1 | [19 empty] | 20 | bar: 2018-11-28 to 2018-11-28
| — Gameplay & Scoring — | [25 empty] | 21
2 | Score System | J | 2 | 3 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 22
2 | Spawning System | J | 3 | 3 | 0 |  | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 23
[5 empty] | 1 | [21 empty] | 24 | bar: 2018-11-28 to 2018-11-28
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Sprint Settings – Only change cells with dark gray borders | [7 empty] | 2018-11-28: Workdays |  | 101
| Justin | J |  | Start Date | 2018-11-28 |  |  | 2018-11-28: Sun; 2018-11-28: 0; 2018-11-28: 0 |  | 102
| Tom | T |  | End Date | 2016-12-21 |  |  | 2018-11-28: Mon; 2018-11-28: 1; 2018-11-28: 1 |  | 103
[8 empty] | 2018-11-28: Tue; 2018-11-28: 1; 2018-11-28: 1 |  | 104
|  |  |  | Total Days | -707 |  |  | 2018-11-28: Wed; 2018-11-28: 1; 2018-11-28: 1 |  | 105
|  |  |  | Work Days | 0 |  |  | 2018-11-28: Thu; 2018-11-28: 1; 2018-11-28: 1 |  | 106
[8 empty] | 2018-11-28: Fri; 2018-11-28: 1; 2018-11-28: 3 |  | 107
| All | ALL | [5 empty] | 2018-11-28: Sat; 2018-11-28: 0; 2018-11-28: 0 |  | 108
| Unassigned | [25 empty] | 109
| Days to Look Back for Burndown Velocity | 2 | [24 empty] | 110
Interpreted Data – DO NOT CHANGE ANYTHING HERE | [26 empty] | 111
| Current Hours Remaining |  |  |  |  | Days | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 112
[6 empty] | On-Track Line | 37 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | 113
114
[6 empty] | Sum | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 115
| Rank (and not reduced to 0 after today) | [25 empty] | 116
| Rank 1 - The MOST important | 1 |  |  |  | Rank 1 | 17 | 17 | 15 | 14 | 12 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 |  | 117
|  | 2 |  |  |  | Rank 2 | 15 | 14 | 13 | 13 | 13 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 118
|  | 3 |  |  |  | Rank 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 119
|  | 4 |  |  |  | Rank 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120
| Rank 5 - The LEAST important | 5 |  |  |  | Rank 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 121
[6 empty] | Sum | 37 | 36 | 33 | 32 | 30 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 |  | 122
123
[6 empty] | Justin | 16 | 15 | 14 | 13 | 13 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 |  | 124
[6 empty] | Tom | 19 | 19 | 19 | 19 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 |  | 125
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 126
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 127
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 128
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 129
[6 empty] | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 130
[6 empty] | Unassigned | 3 | 3 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 131
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 132
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 133
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 134
135
[5 empty] | Team | 2 | [20 empty] | 136
[7 empty] | 0 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 |  | 137
[6 empty] | Average Assigned | 19 | 18.5 | 17 | 16.5 | 15.5 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 |  | 138
[6 empty] | On-Track Line | 18.5 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | 139
[7 empty] | 0 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 |  | 140
141
[7 empty] | 2018-11-27 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 |  | 142
| Total Hours | 37 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 143
| Hours 2 Days Ago | #N/A |  |  |  |  | 37 | 36 | 33 | 32 | 30 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 |  | 144
| Hours Today | #N/A |  |  |  | Burndown Velocity |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | 145
| Today | #N/A |  |  |  | BDV | 2018-11-27: #N/A |  | 146
147
148
149
150

## Daily Scrum
2016-12-13 |  | Team Members
Dates |  | Justin | Tom |  |  | Workday
2018-11-28 | Wed | Yesterday: Prokect Kickoff Today: Acceleration Help: – Nothing now | Yesterday: Project Kickoff Today: Collisions Help: – | Yesterday: Project Kickoff Today: I'm out of town until 12/13 Help: – | Yesterday: Project Kickoff Today: No time today H: – | 1
2018-11-29 | Thu | Y: About 25% of Accel T: – Not able to work today H: – | Y: Collisions about 25% done T: More collisions H: – | Y: – T: Still out of town. Call if you need anything (555) 867-5309. H: – | Y: – T: Follow cam (delayed car angling tracking thing) H: – | 1
2018-11-30 | Fri | Y: – T: Acceleration tuning H: Something feels wrong about the acceleration. I could use some help. | Y: Collisions at about 50% now T: I have a little time to help Archon H: – | Y: – T: – H: – |  | 1
2018-12-01 | Sat |  |  |  |  | 0
2018-12-02 | Sun |  |  |  |  | 0
2018-12-03 | Mon | Y: (Fri) Got help from Henri with acceleration. It's at about 50% now. T: Speed management. H: – | Y: Didn't do any of my work because Acceleration issues took all my time. T: – Out for the next three days H: – | Y: – T: Back tomorrow. H: – |  | 1
2018-12-04 | Tue | Y: Speed 50% complete T: More accel; hopefully finishing. H: – |  | Y: – T: Finally back! Working on Point System. H: If someone could help get me back up to speed, I'd appreciate it. | Y: – T: Risky driving system H: – | 1
2018-12-05 | Wed |  |  |  |  | 1
2018-12-06 | Thu |  |  |  |  | 1
2018-12-07 | Fri |  |  |  |  | 1
2018-12-08 | Sat |  |  |  |  | 0
2018-12-09 | Sun |  |  |  |  | 0
2018-12-10 | Mon |  |  |  |  | 1
2018-12-11 | Tue |  |  |  |  | 1
2018-12-12 | Wed |  |  |  |  | 1
2018-12-13 | Thu |  |  |  |  | 1
2018-12-14 | Fri |  |  |  |  | 1
2018-12-15 | Sat |  |  |  |  | 0
2018-12-16 | Sun |  |  |  |  | 0
2018-12-17 | Mon |  |  |  |  | 1
2018-12-18 | Tue |  |  |  |  | 1
2018-12-19 | Wed |  |  |  |  | 1